## Project Plan
Project Plan: File Storage Transition
Task ID | Task | Owner | Start Date | Due Date | Status | Priority | Notes
P-001 | Map current shared-drive folders | Priya Shah | 2026-09-16 | 2026-09-23 | In progress | High | Identify team-owned content
P-002 | Agree OneDrive guidance for personal drafts | Alex Morgan | 2026-09-18 | 2026-09-25 | Not started | Medium | Use simple examples
P-003 | Create department Team folder structure | Daniel Reed | 2026-09-23 | 2026-09-30 | Not started | High | Avoid overcomplicated folders
P-004 | Move active meeting documents | Sarah Jones | 2026-09-30 | 2026-10-07 | Not started | Medium | Keep archive separate
P-005 | Publish final staff procedures | Priya Shah | 2026-10-07 | 2026-10-14 | Blocked | High | Waiting for approval
P-006 | Review sharing permissions | Daniel Reed | 2026-10-14 | 2026-10-21 | Not started | Medium | Check view/edit defaults
P-007 | Collect staff feedback | Alex Morgan | 2026-10-21 | 2026-10-28 | Not started | Low | Short feedback form
Quick view | Count
Not started | 5
In progress | 1
Blocked | 1
Complete | 0